## Slide 1: Multiple Cooks in the Kitchen: Successful Navigation of a Multi-Collaborator GoldSim Modeling Project
Paul Haby*, WSP USA
Steve Byers, WSP USA
Alyssa Seal, WSP USA
Dan Walker, WSP Canada
* Presenting Author - Paul.Haby@wsp.com

## Slide 2: Introductory Acknowledgements
WSP presentation collaborators:
  Steve Byers, WSP USA
  Alyssa Seal, WSP USA
  Dan Walker, WSP Canada
External Project collaborators for the many hours of coordinating conversations and the many ideas that led to the development and implementation of this collaborative approach and ultimately the successful completion of this Project.
Confidential client for providing the opportunity to be involved in this unique and interesting Project.

## Slide 3: Collaborative Modeling Case Study

## Slide 4: Mission:
Build a flexible, site-wide water balance and water quality model for a Mine with two distinct Project areas and downstream receiving environment assessments
Seems reasonably straightforward…right?
Except……..

## Slide 5
Rather than a single entity building the entire model in-house, each of the two facility components are to be developed in parallel by separate model developers!
This calls for a different approach!

## Slide 6: The Challenges
How to structure the model development process?
  The Project timeline would not allow for sequential development of each model component – component development needed to be done in parallel.
How to accommodate updates to model inputs?
  All model components need to use the most current inputs which might continue to change over the course of a rapidly developing Project
How can separately-developed model components be readily combined?
  Issues related to simulation settings, array definitions, etc.
  Need for seamless two-way updates as components continue to be refined:
    Primary model input updates to model component developers
    Component updates to the main model

## Slide 7: A Multi-Pronged Approach:
“Conceptual responsibility” diagrams
Model development and integration playbook
  Clearly defines the objectives for the final model deliverable
  Contains specifications and details to coordinate model development and operation among the multiple collaborators
A shared, GoldSim-based subset of the larger model dubbed the “Framework” or “Framework Component” Containing
  Simulation settings
  Global variables and scenarios
  Global inputs and inputs needed for the externally-developed components

## Slide 8: Conceptual Responsibility Diagrams

## Slide 9: Conceptual Responsibility Diagrams
Similar to standard conceptual process diagrams, but…
Defined regions of collaborator responsibility
  Indicated via background color shading
Defined model connection or “tie-in” points for integration of model components
  Pre-defined (thus standardized) nomenclature
  Shown between designated areas of responsibility (non-shaded areas)
  Color-coded labels to indicate responsibility

## Slide 10: Conceptual Responsibility Diagram: Mine Facility 1

## Slide 11: Conceptual Responsibility Diagram: Mine Facility 2

## Slide 12: Model Integration Playbook

## Slide 13: Model Integration Playbook: Change Log

## Slide 14: Model Integration Playbook: Simulation Settings

## Slide 15: Model Integration Playbook: Model Array Definitions
1) The species array was provided in the initial distribution of the Framework, but was then moved outside the Framework container due to the CT Module’s Material container. Subsequent updates to the species array were communicated to collaborators who manually made the updates to their local version of the Material container.

## Slide 16: Model Integration Playbook: Nomenclature

## Slide 17: Model Integration Playbook: Flow IDs and Responsibilities

## Slide 18: Model Integration Playbook:

## Slide 19: Framework

## Slide 20: Framework
A shared subset of the larger model containing:
  Simulation settings
  Global variables and scenarios
  Global inputs
Developed and maintained by lead model integrator based on input from Project stakeholders
Provides for consistency of model time and simulation settings, inputs, scenarios, etc. across Project collaborators
Readily swappable into collaborator component models as updates become available

## Slide 21: Recall:

## Slide 22: Use of Framework for Multi-Collaborator, Parallel Model Development

## Slide 25: Additional Considerations

## Slide 26: Approach to Successful Collaboration
Proactively engage with Client and Collaborators to define the scope and objectives of the model
Collaboratively develop a clear understanding of the scope and battery limits for all model contributors early in the process, and get acknowledged agreement
Regular and frequent alignment meetings with model contributors, particularly early in the process
  Collaborative discussion of proposed changes to conceptual responsibility diagrams, model playbook, and framework
  Meeting agenda to guide contributor meetings and circulated meeting notes with clear actions items and defined responsibilities are critical
Regular dissemination of updates to collaborators
  Lead integrator maintains master documents
  Issuance of updates to the framework along with the integration playbook and conceptual responsibility diagrams
  Provide clear information on exactly what has changed in the updates and what steps need to be taken to implement the changes
  Versioning of updates and documentation of changes to avoid confusion and use of outdated versions

## Slide 27: GoldSim-Specific Considerations for Collaborative Modeling
Pre-determination and alignment of simulation settings
  Prevent the possibility of different results for models run under different time settings (unscheduled updates, etc.)
  Common simulation length, time steps, reporting periods, Monte Carlo sampling sequence, etc.
No clones (minimize the potential for broken clones during component integration)
No localization of containers with model tie-ins
  Prevent the possibility of needing to re-expose outputs
  Prevent renaming exposed output aliases, possibly leading to confusion and incorrect linkages
Pre-defined arrays – mismatching array labels will impede component integration
Consideration of GoldSim module availability and use among collaborators:
  Special case for CT/RT Material container – cannot be copied or replaced
  Agreement on Solution Precision setting if using Contaminant Transport/Radionuclide Transport modules

## Slide 28: Applicability to In-House Modeling Projects
The approaches and techniques used in the execution of this Project are not limited to projects with external collaborators
Application to in-house modeling projects:
  Delegation and management of model component development responsibilities within a modeling team
  Development of specialized model components by others outside the primary modeling team
  Parallel development of model components to accelerate project timelines compared to a linear development approach

## Slide 29: Conclusion
In what could have potentially become a case of “too many cooks”, this case study instead highlights a successful approach to the parallel development of model components by multiple collaborators
Keys to success:
  Collaborative mindset
  Meticulous pre-planning and regular and frequent coordination across all collaborators
  Pre-mapping of responsibilities with an acknowledged understanding of roles, scope, and integration tie-ins
  Detailed model development and integration plan
  Shared common GoldSim framework to align component development

## Slide 30: La Fin!